## Blog
ID | Theme | Title | Assigned To | Time Estimate (hours) | Actual Time | Status | Comments
10 | Materials | Delete Materials | jiamin | 4 | 5 | Complete
10 | Materials | Update Materials | jiamin | 4 | 5 | Complete
11 | Patron | Add Patron | yile | 12 | 8 | Complete
11 | Patron | Delete Patrons | yile | 4 | 3 | Complete
11 | Patron | Update Patrons | yile | 4 | 5 | Complete
6 | Site security | Librarian log in | Zhe | 8 | 4 | Accetable | Finish too early and still need to adapt to the new pages
18 | Site security | Patron log in | zhe | 2 | 4 | Complete
8 | Check In/Out | Material Check-out | yile | 12 | 12 | Complete
8 | Optional | Valid material ID-checkout | Yile | 4 | 2 | Complete
9 | Check In/Out | Material Check-in | yile | 12 | 5 | Complete
8 | Optional | Valid patron ID | Yile | 6 | 2 | Complete
27 | Check In/Out | Manual overdue report | Yile | 12 | 1 | Complete
12 | Search | Librarian materials search | jiamin/yile | 12 | 13 | Complete | First finished in apr 13, but with database chagne, redo on apr 27
13 | Search | Librarian patron search | yile | 12 | 0.5 | Complete
15 | Search | Public material search | jiamin/yile(serach function lost) | 4 | 5.5 | Accetable | search function broken after merge, Still working on searching on master page
22 | Search | Patron material search | yile | 2 | 3 | Complete
8 | Optional | Patron view overdue items | Yile | 4 | 2 | Complete | The patron can view their overdue items
17 | Mobile | Mobile device contact | zhe | 8 | 12 | Complete | Nearlly done , adjust the interface, may need more hours
17 | Mobile | Mobile device search | zhe | 4 | 4 | Complete | Nearlly done , adjust the interface
10 | Materials | Add Materials | Jiamin/Yile | 12 | 10 | Complete | First finished in apr 13, but with database chagne, redo on apr 29
10 | Optional | Valid added material | Yile | 2 | 1 | Complete
8 | Optional | Check out limitation | Yile | 2 | 0.5 | Complete
| Non-functional | Site design | jiamin/yile | 4 | 35 | Accetable | Still have problems with small detials , like required fields,delete confirmation
| Non-functional | Document | Yile/Jiamin/Zhe | 20 | 35 | Complete
Another task
Another task

## Burndown Chart
Iteration 1 |  |  | Work Date | Work Day | Ideal Remaining Effort | Actual Remaining Effort | Completed Hours Zhe | Completed Hours Jiamin | Completed Hour Yile | Man Hours Daily used | Total man use | Daily CompletedTask | Total task complete | Me hour Used | Calculated Efficiency Factor
Start Date | 2013-04-13 |  |  | 0 | 171.5 | 171.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 0
End Date | 2013-05-07 |  | 2013-04-02 | 1 | 166.628 | 171.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 13.92 | 0
# of Developers | 3 |  | 2013-04-03 | 2 | 161.756 | 171.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 20.88 | 0
Efficiency Factor | 0.7 |  | 2013-04-04 | 3 | 156.884 | 171.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 27.84 | 0
Work Hours | 245 |  | 2013-04-05 | 4 | 152.012 | 171.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 34.8 | 0
Effective Man Hour | 171.5 |  | 2013-04-06 | 5 | 147.14 | 171.5 | 0 | 0 | 0 | 2 | 2.5 | 0 | 0 | 41.76 | 0
Hour per day | 2.32 |  | 2013-04-07 | 6 | 142.268 | 171.5 | 0 | 0 | 0 | 12 | 14.5 | 0 | 0 | 48.72 | 0
Ideal effective hour Per day | 1.624 |  | 2013-04-08 | 7 | 137.396 | 171.5 | 0 | 0 | 0 | 0 | 14.5 | 0 | 0 | 55.68 | 0
Ideal Remaining Effort | 0.98 |  | 2013-04-09 | 8 | 132.524 | 161.5 | 0 | 10 | 0 | 10 | 24.5 | 10 | 10 | 62.64 | 0.15964
|  |  | 2013-04-10 | 9 | 127.652 | 161.5 | 0 | 0 | 0 | 2.5 | 27 | 0 | 10 | 69.6 | 0.14368
|  |  | 2013-04-11 | 10 | 122.78 | 161.5 | 0 | 0 | 0 | 0 | 27 | 0 | 10 | 76.56 | 0.13062
|  |  | 2013-04-12 | 11 | 117.908 | 161.5 | 0 | 0 | 0 | 2 | 29 | 0 | 10 | 83.52 | 0.11973
|  |  | 2013-04-13 | 12 | 113.036 | 161.5 | 0 | 0 | 0 | 4 | 33 | 0 | 10 | 90.48 | 0.11052
Delete Materials | 4 | Complete | 2013-04-14 | 13 | 108.164 | 155.5 | 2 | 0 | 4 | 10 | 43 | 6 | 16 | 97.44 | 0.1642
Update Materials | 4 | Complete | 2013-04-15 | 14 | 103.292 | 145.5 | 4 | 0 | 6 | 5 | 48 | 10 | 26 | 104.4 | 0.24904
Add Patron | 12 | Complete | 2013-04-16 | 15 | 98.42 | 131.5 | 4 | 0 | 10 | 10 | 58 | 14 | 40 | 111.36 | 0.3592
Delete Patrons | 4 | Complete | 2013-04-17 | 16 | 93.548 | 125.5 | 0 | 0 | 6 | 8 | 66 | 6 | 46 | 118.32 | 0.38878
Update Patrons | 4 | Complete | 2013-04-18 | 17 | 88.676 | 115.5 | 0 | 0 | 10 | 10 | 76 | 10 | 56 | 125.28 | 0.447
Librarian log in | 8 | Accetable | 2013-04-19 | 18 | 83.804 | 105.5 | 0 | 0 | 10 | 0 | 76 | 10 | 66 | 132.24 | 0.49909
Patron log in | 2 | Complete | 2013-04-20 | 19 | 78.932 | 85.5 | 0 | 0 | 20 | 9 | 85 | 20 | 86 | 139.2 | 0.61782
Material Check-out | 12 | Complete | 2013-04-21 | 20 | 74.06 | 85.5 | 0 | 0 | 0 | 0 | 85 | 0 | 86 | 146.16 | 0.5884
Valid material ID-checkout | 4 | Complete | 2013-04-22 | 21 | 69.188 | 85.5 | 0 | 0 | 0 | 2 | 87 | 0 | 86 | 153.12 | 0.56165
Material Check-in | 12 | Complete | 2013-04-23 | 22 | 64.316 | 85.5 | 0 | 0 | 0 | 2.5 | 89.5 | 0 | 86 | 160.08 | 0.53723
Valid patron ID | 6 | Complete | 2013-04-24 | 23 | 59.444 | 85.5 | 0 | 0 | 0 | 2 | 91.5 | 0 | 86 | 167.04 | 0.51485
Manual overdue report | 12 | Complete | 2013-04-25 | 24 | 54.572 | 85.5 | 0 | 0 | 0 | 4 | 95.5 | 0 | 86 | 174 | 0.49425
Librarian materials search | 12 | Complete | 2013-04-26 | 25 | 49.7 | 85.5 | 0 | 0 | 0 | 8 | 103.5 | 0 | 86 | 180.96 | 0.47524
Librarian patron search | 12 | Complete | 2013-04-27 | 26 | 44.828 | 67.5 | 6 | 10 | 2 | 4.5 | 108 | 18 | 104 | 187.92 | 0.55343
Public material search | 4 | Accetable | 2013-04-28 | 27 | 39.956 | 67.5 | 0 | 0 | 0 | 4 | 112 | 0 | 104 | 194.88 | 0.53366
Patron material search | 2 | Complete | 2013-04-29 | 28 | 35.084 | 41.5 | 2 | 10 | 14 | 11 | 123 | 26 | 130 | 201.84 | 0.64407
Patron view overdue items | 4 | Complete | 2013-04-30 | 29 | 30.212 | 27.5 | 4 | 0 | 10 | 7.5 | 130.5 | 14 | 144 | 208.8 | 0.68966
Mobile device contact | 8 | Complete | 2013-05-01 | 30 | 25.34 | 27.5 | 0 | 0 | 0 | 8 | 138.5 | 0 | 144 | 215.76 | 0.66741
Mobile device search | 4 | Complete | 2013-05-02 | 31 | 20.468 | 25.5 | 0 | 0 | 2 | 5 | 143.5 | 2 | 146 | 222.72 | 0.65553
Add Materials | 12 | Complete | 2013-05-03 | 32 | 15.596 | 25.5 | 0 | 0 | 0 | 0 | 143.5 | 0 | 146 | 229.68 | 0.63567
Valid added material ID | 2 | Complete | 2013-05-04 | 33 | 10.724 | 25.5 | 0 | 0 | 0 | 8 | 151.5 | 0 | 146 | 236.64 | 0.61697
Check out limitation | 2 | Complete | 2013-05-05 | 34 | 5.852 | 25.5 | 0 | 0 | 0 | 4 | 155.5 | 0 | 146 | 243.6 | 0.59934
Site design | 4 | Accetable | 2013-05-06 | 35 | 0.98 | 25.5 | 0 | 0 | 0 | 10 | 165.5 | 0 | 146 | 250.56 | 0.58269
Document | 20 | Complete | 2013-05-07 | end | -3.892 | 1.5 | 8 | 8 | 8 | 12 | 177.5 | 24 | 170 | 257.52 | 0.66014
Total Assignment Task Hours | 170
Available Time - Assigned time | -3.892